## TIMELINE TEMPLATE
TIMELINE | 18+ MO. PRIOR | 15 MO. PRIOR | 12-6 MO. PRIOR | 3+ MO PRIOR | 2 MO. PRIOR | 1 MO. PRIOR | 1 WK PRIOR | EVENT DATE | 1 MO. POST | 3+ MO. POST | NOTES
MILESTONES | Explore course ideas | Submit pre-approval app request to CME Advisory Exec Comm | Submit accreditation application & projected budget to CME committee | Review course financial statement |  |  |  | SHOWTIME |  | SUBMIT FINAL COURSE REPORT
PROGRAM | Identify course need | Identify outcomes Document Needs assessment; Develop Objectives; Outline Content | Confirm faculty & complete program schedule | Define outcomes confirm program | Prepare evaluation | presentations slides/video submitted to ICME for ACCME compliance review |  | SHOWTIME | Summarize evals + test data | Deploy post activity Follow Up survey; wrap up outcomes; prepare course file for retention
FINANCIAL |  | Estimate projected budget | Complete projected budget | M A N A G E F I N A N C I A L S ---------------------------------------> All funds must be handled through ICME. No direct payments from commerical interests to speakers or vendors! |  |  |  |  | Reconcile expenses/ complete exp report
M A N A G E I N D U S T R Y S U P P O R T ----------------------------------------------->
INDUSTRY |  | Identify potential industry support | Send grant & exhibitor requests to industry | [5 empty] | Reconcile industry support
I M P L E M E N T M A R K E T I N G S T R A T E G Y ------------------------------------>
MARKETING |  | Design marketing strategy | Implement marketing strategy- send SAVE THE DATE | Send eblast & snail mail program flyers
LOGISTICS | Identify planning committee/ initiate site selection | Clear possible dates with ICME; Reserve conf location; Complete site contract; room reservations; outline AV needs | Manage faculty: get disclosures, advise slide prep + review, test questions, etc; Coordinate registration; book hotel reservations for faculty | Confirm vendor contracts - LOA + Exhibitor agreements | Review set up; manage registration; order course materials | Confirm set up, food &bev needs; print course materials; confirm vendor details; all videos/slides submitted to ICME for review | Print CME info sheet, assemble folders, nametags |  | Send outcomes summaries to course director; compile post course highlights
TECHNOLOGY |  |  | Outline technology needs |  |  | Confirm AV details | Pre-load slides